## Sheet1
# | Tasks | How Long | End Date | Status | Who?
1 | Define and Agree to Working Agreement | 40 mins | 2024-09-30 | Finished | Team
2 | Version control system | 10 - 15 mins | 2024-09-20 | Finished | Ciarán
3 | User Stories | 10hrs | 2024-09-30 | Finished | Team
4 | Design database | 2hrs |  | In Progress | Dimitrije
5 | Define System Architecture | 30mins |  | Not Started
6 | Set up Development Environment | 15 mins |  | Not Started
7 | Make Customer table in database |  |  | Not Started
8 | Make Order table in database |  |  | Not Started
9 | Make Delivery Area table in database |  |  | Not Started
10 | Make Publications table in database |  |  | Not Started
11 | Make Delivery Driver table in database |  |  | Not Started
12 | Make Invoice table in database |  |  | Not Started
13 | Make Delivery Docket table in database |  |  | Not Started
14 | Design Customer UML | 30mins |  | Not Started
15 | Design Order UML | 30mins |  | Not Started
16 | Design Delivery Area UML | 30mins |  | Not Started
17 | Design Publications UML | 30mins |  | Not Started
18 | Design Invoice UML | 30mins |  | Not Started
19 | Design Delivery Driver UML | 30mins |  | Not Started
20 | Design Delivery Docket UML | 30mins |  | Not Started
21 | Design Junit tests(Customer class)
22 | Design Junit tests(Delivery area class)
23 | Design Junit tests(Delivery Docket class)
24 | Design Junit tests(Invoice class)
25 | Design Junit tests(Publciations class)
26 | Design Junit tests( Order class)
27 | Design Junit tests(Delivery Driver class)
28 | Develop Customer class
29 | Develop Invoice class
30 | Develop Order class
31 | Develop Publications class
32 | Develop Delivery Area class
33 | Develop Delivery Driver class
34 | Develop Delivery Docket class
35 | Conduct Junit tests(Customer class)
36 | Conduct Junit tests(Delivery area class)
37 | Conduct Junit tests(Delivery Docket class)
38 | Conduct Junit tests(Invoice class)
39 | Conduct Junit tests(Publciations class)
40 | Conduct Junit tests( Order class)
41 | Conduct Junit tests(Delivery Driver class)
42